## Business Case
General Request Information
Request/Contract Name:
Requester:
Business Owner:
Requester Phone Number:
Request Description
What is your Business or User Need?: Provide a brief description of the business need/issue/problem that the requested project will address and why you are proposing a new IT solution to meet this business need rather than meeting the need within existing resources. (2000 character limit)
Summary of Current Solution: Describe how your project will meet the business need and the resources involved. (2000 character limit)
How will CMS Benefit from this effort?: Provide a summary of how this effort benefits CMS. Include any information on how it supports CMS' mission, creates efficiencies and/or cost savings, or reduces risk. (2000 character limit)
Does this effort align with any Organizational Priorities?: Does this effort support any Administrator priorities or new legislative or regulatory mandates? Include any relevant deadlines. (2000 character limit)
How will you determine whether or not this effort is Successful? Include any performance indicators that you think would demonstrate improved business outcomes - ie. because of this effort, WHO is going to do exactly WHAT, by exactly HOW MUCH, by exactly WHEN? (2000 character limit)
Alternatives Analysis
Below you should identify options and alternatives to meet your business need. Include a summary of the approaches, how you get the solution, and describe the pros, cons, total life cycle costs and potential cost savings/avoidance for each alternative considered. Include at least three viable alternatives, starting with your preferred solution. You should not describe the proposed solutions in technical detail, but instead should describe the "alternative concepts", such as: • Buying a Commercial off the shelf (COTS) product/tool vs. • Buying a Government off the shelf (GOTS) product/tool vs. • Developing a Custom-built solution vs. • Using/repurposing an existing CMS system vs. • Using an Enterprise Shared Service In your alternatives, include details such as differences between system capabilities, user friendliness, technical and security considerations, ease and timing of integration with CMS' IT infrastructure, etc.
Preferred Solution
Preferred solution: Title
Preferred solution: Summary (2000 character limit)
Preferred solution: Acquisition Approach: Describe the approach to acquiring the products and services required to deliver the solution, including potential contract vehicles. (2000 character limit)
Is your solution approved by IT Security for use at CMS (FedRAMP, FISMA approved, within the CMS cloud enclave)?:
Yes/No
If Above Answer is No - Is it in the process of CMS approval?: (Obtaining CMS Approval can be lengthy and solutions that do not have it or are just starting may lead to longer project timelines.)
Yes/No/I'm not sure
Do you need to host your solution and where?: (Cloud - AWS, Azure, etc. or a Data Center). What, if any, type of cloud service are you planning to use for this solution (Iaas, PaaS, SaaS, etc.)?
Will your solution have a User Interface?:
Yes/No/I'm not sure
Preferred solution: Pros (2000 character limit)
Preferred solution: Cons (2000 character limit)
Estimated Life Cycle Costs: Cost estimates should account for all costs related to the development of your initial solution, as well as the cost to operate and maintain that solution. Related costs include any impacts on other services/contracts outside your immediate contract, such as component/enterprise services, tools, pilots, etc. paid for separately by your component, OIT, or others to help meet your business need – include these under “other” costs.
| FY 2023 Estimated Cost | FY 2024 Estimated Cost | FY 2025 Estimated Cost | FY 2026 Estimated Cost | FY 2027 Estimated Cost | 5-Year Estimated Costs
Development | [5 empty] | 0
Operations and Maintenance | [5 empty] | 0
Other | [5 empty] | 0
Other | [5 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0
What is the Cost Savings or Avoidance associated with this solution?: Provide a brief description of any potential cost savings that this solution might provide and/or cost avoidance, which describes money that you will need to spend if the solution isn't implemented. This could include old systems going away, contract hours/new FTEs not needed, or other savings, even if indirect. (2000 character limit)
Alternative A
Alternative A: Title
Alternative A: Summary (2000 character limit)
Alternative A: Acquisition Approach: Describe the approach to acquiring the products and services required to deliver the solution, including potential contract vehicles. (2000 character limit)
Is your solution approved by IT Security for use at CMS (FedRAMP, FISMA approved, within the CMS cloud enclave)?:
Yes/No
If Above Answer is No - Is it in the process of CMS approval?: (Obtaining CMS Approval can be lengthy and solutions that do not have it or are starting may lead to longer project timelines.)
Yes/No/I'm not sure
Do you need to host your solution and where?: (Cloud - AWS, Azure, etc. or a Data Center). What, if any, type of cloud service are you planning to use for this solution (Iaas, PaaS, SaaS, etc.)?
Will your solution have a User Interface?:
Yes/No/I'm not sure
Alternative A: Pros (2000 character limit)
Alternative A: Cons (2000 character limit)
Estimated Life Cycle Costs: Cost estimates should account for all costs related to the development of your initial solution, as well as the cost to operate and maintain that solution. Related costs include any impacts on other services/contracts outside your immediate contract, such as component/enterprise services, tools, pilots, etc. paid for separately by your component, OIT, or others to help meet your business need – include these under “other” costs.
| FY 2023 Estimated Cost | FY 2024 Estimated Cost | FY 2025 Estimated Cost | FY 2026 Estimated Cost | FY 2027 Estimated Cost | 5-Year Estimated Costs
Development | [5 empty] | 0
Operations and Maintenance | [5 empty] | 0
Other | [5 empty] | 0
Other | [5 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0
What is the Cost Savings or Avoidance associated with this solution?: Provide a brief description of any potential cost savings that this solution might provide and/or cost avoidance, which describes money that you will need to spend if the solution isn't implemented. This could include old systems going away, contract hours/new FTEs not needed, or other savings, even if indirect. (2000 character limit)
Alternative B
Alternative B: Title
Alternative B: Summary (2000 character limit)
Alternative B: Acquisition Approach: Describe the approach to acquiring the products and services required to deliver the solution, including potential contract vehicles. (2000 character limit)
Is your solution approved by IT Security for use at CMS (FedRAMP, FISMA approved, within the CMS cloud enclave)?:
Yes/No
If Above Answer is No - Is it in the process of CMS approval?: (Obtaining CMS Approval can be lengthy and solutions that do not have it or are starting may lead to longer project timelines.)
Yes/No/I'm not sure
Do you need to host your solution and where?: (Cloud - AWS, Azure, etc. or a Data Center). What, if any, type of cloud service are you planning to use for this solution (Iaas, PaaS, SaaS, etc.)?
Will your solution have a User Interface?:
Yes/No/I'm not sure
Alternative B: Pros (2000 character limit)
Alternative B: Cons (2000 character limit)
Estimated Life Cycle Costs: Cost estimates should account for all costs related to the development of your initial solution, as well as the cost to operate and maintain that solution. Related costs include any impacts on other services/contracts outside your immediate contract, such as component/enterprise services, tools, pilots, etc. paid for separately by your component, OIT, or others to help meet your business need – include these under “other” costs.
| FY 2023 Estimated Cost | FY 2024 Estimated Cost | FY 2025 Estimated Cost | FY 2026 Estimated Cost | FY 2027 Estimated Cost | 5-Year Estimated Costs
Development | [5 empty] | 0
Operations and Maintenance | [5 empty] | 0
Other | [5 empty] | 0
Other | [5 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0
What is the Cost Savings or Avoidance associated with this solution?: Provide a brief description of any potential cost savings that this solution might provide and/or cost avoidance, which describes money that you will need to spend if the solution isn't implemented. This could include old systems going away, contract hours/new FTEs not needed, or other savings, even if indirect. (2000 character limit)

## Business Case - Example
General Request Information
Request/Contract Name: | Workflow Improvement Project (WIP)
Requester: | Jane Doe
Business Owner: | John Smith
Requester Phone Number: | 410-786-xxxx
Request Description
What is your Business or User Need?: Provide a brief description of the business need/issue/problem that the requested project will address and why you are proposing a new IT solution to meet this business need rather than meeting the need within existing resources. (2000 character limit)
Currently ICPG has a manual process to track the number of widgets used in the IT capital planning process. This requires a team of five people to count, identify, and invoice for the widgets, taking approximately 30 hours per person, per week and taking away from other duties, and in particular hours that will be needed as a result of the new FORM Act, which will double our workload starting in two years. We believe that an automated IT solution will reduce the current workload, freeing up staff resources and streamlining our processes to accomodate the FORM Act.
Summary of Current Solution: Describe how this business need will meet the business need and the resources involved. (2000 character limit)
Currently ICPG has a manual tedious process to track the number of widgets used in the IT capital planning process. This requires a team of five people to count, identify, and invoice for the widgets, taking approximately 30 hours per person, per week. When the FORM Act doubles our workload, 150 new FTE hours per week will be needed, necessitating four new FTEs. Due to our manual processes, CMS decision makers do not have the information that they need to make capital planning decisions.
How will CMS Benefit from this effort?: Provide a summary of how this effort benefits CMS. Include any information on how it supports CMS' mission, creates efficiencies and/or cost savings, or reduces risk. (2000 character limit)
The IT capital planning process is the agency's means of ensuring that our IT Investments are a wise use of CMS resources, meeting business needs at acceptable costs and without duplication. The capital planning process relies on widgets as an input to the process in order to inform decision makers. Due to our manual processes, there is a widget tracking backlog, meaning CMS decision makers do not have the information that they need to make capital planning decisions. Meeting this business need will allow CMS to make better decisions and manage our IT portfolio more cost effectively, saving the agency money.
Does this effort align with any Organizational Priorities?: Does this effort support any Administrator priorities or new legislative or regulatory mandates? Include any relevant deadlines. (2000 character limit)
This effort aligns with the Agency modernization initiative and also supports FITARA and FORM Act implementation.
How will you determine whether or not this effort is Successful? Include any performance indicators that you think would demonstrate improved business outcomes - ie. because of this effort, WHO is going to do exactly WHAT, by exactly HOW MUCH, by exactly WHEN? (2000 character limit)
With our preferred solution, we expect that the number of FTE hours required to track widgets will decrease our current workload by 75%. Even with the FORM Act doubling our workload, this would still equate to a total FTE hour reduction of 50%, if the process is fully automated.
Alternatives Analysis
Below you should identify options and alternatives to meet your business need. Include a summary of the approaches, how you will acquire the solution, and describe the pros, cons, total life cycle costs and potential cost savings/avoidance for each alternative considered. Include at least three viable alternatives, starting with your preferred solution. You should not describe the proposed solutions in technical detail, but instead should describe the "alternative concepts", such as: • Buying a Commercial off the shelf (COTS) product/tool vs. • Buying a Government off the shelf (GOTS) product/tool vs. • Developing a Custom-built solution vs. • Using/repurposing an existing CMS system vs. • Using an Enterprise Shared Service In your alternatives, include details such as differences between system capabilities, user friendliness, technical and security considerations, ease and timing of integration with CMS' IT infrastructure, etc.
Preferred Solution
Preferred solution: Title
Enterprise Shared Service: SERVICE NOW
Preferred solution: Summary (2000 character limit)
ServiceNow's workflow process capabilities can be used to route the widget tracking process and automate the identification and counting of the widgets. Their platform is being proposed, utlizing an existing licensing agreement.
Preferred solution: Acquisition Approach: Describe the approach to acquiring the products and services required to deliver the solution, including potential contract vehicles. (2000 character limit)
We are planning to use the current instance of ServiceNow used elsewhere in OIT.
Is your solution approved by IT Security for use at CMS (FedRAMP, FISMA approved, within the CMS cloud enclave)?:
Yes
If Above Answer is No - Is it in the process of CMS approval?: (Obtaining CMS Approval can be lengthy and solutions that do not have it or are just starting may lead to longer project timelines.)
N/A
Do you need to host your solution and where?: (Cloud - AWS, Azure, etc. or a Data Center). What, if any, type of cloud service are you planning to use for this solution (Iaas, PaaS, SaaS, etc.)?
CMS AWS Cloud Instance - SaaS - ServiceNow; IaaS - AWS
Will your solution have a User Interface?:
Yes
Preferred solution: Pros (2000 character limit)
This solution can be accomplished prior to the end of the fiscal year, is user-friendly, and already meets agency security requirements.
Preferred solution: Cons (2000 character limit)
The solution does not have invoicing capabililties and approximately fifteen hours of staff time per person will still be needed each week to accomplish all tasks, including the FORM Act.
Estimated Life Cycle Costs: Cost estimates should account for all costs related to the development of your initial solution, as well as the cost to operate and maintain that solution. Related costs include any impacts on other services/contracts outside your immediate contract, such as component/enterprise services, tools, pilots, etc. paid for separately by your component, OIT, or others to help meet your business need – include these under “other” costs.
The below costs were estimated in consultation with OIT/ESSG.
| FY 2023 Estimated Cost | FY 2024 Estimated Cost | FY 2025 Estimated Cost | FY 2026 Estimated Cost | FY 2027 Estimated Cost | 5-Year Estimated Costs
Development | 1700000 |  |  |  |  | 1700000
Operations and Maintenance |  | 160000 | 164800 | 169744 | 174836.32 | 669380.32
Other | [5 empty] | 0
TOTAL | 1700000 | 160000 | 164800 | 169744 | 174836.32 | 2369380.32
What is the Cost Savings or Avoidance associated with this solution?: Provide a brief description of any potential cost savings that this solution might provide and/or cost avoidance, which describes money that you will need to spend if the solution isn't implemented. This could include old systems going away, contract hours/new FTEs not needed, or other savings, even if indirect. (2000 character limit)
This solution will reduce widget tracking time needed by about 75%. If implemented, the staff hours freed up will mean that ICPG will not need to request additional staff to implement the FORM Act in two years, translating to $684,000 in cost avoidance in that first year.
Alternative A
Alternative A: Title
Buy COTS Tool: ATLASSIAN
Alternative A: Summary (2000 character limit)
Atlassian's workflow process capabilities can be used to route the widget tracking process and automate the identification, counting, and invoicing of the widgets. Their platform is being proposed, to be housed in AWS.
Alternative A: Acquisition Approach: Describe the approach to acquiring the products and services required to deliver the solution, including potential contract vehicles. (2000 character limit)
This will be a new procurement, using OAGM's preferred contract vehicle.
Is your solution approved by IT Security for use at CMS (FedRAMP, FISMA approved, within the CMS cloud enclave)?:
No
If Above Answer is No - Is it in the process of CMS approval?: (Obtaining CMS Approval can be lengthy and solutions that do not have it or are just starting may lead to longer project timelines.)
Not Yet
Do you need to host your solution and where?: (Cloud - AWS, Azure, etc. or a Data Center). What, if any, type of cloud service are you planning to use for this solution (Iaas, PaaS, SaaS, etc.)?
Microsoft Azure Government Cloud - Saas - Atlassian; IaaS - MAG
Will your solution have a User Interface?:
Yes
Alternative A: Pros (2000 character limit)
This solution can perform the entirety of the widget processing workflow, including invoicing, thereby reducing staff time to approximately twelve hours per week per person to accomplish all tasks, including the FORM Act.
Alternative A: Cons (2000 character limit)
This solution will have higher operational costs than the other alternatives. We are unsure of the onboarding process for Microsoft Azure Government and what the ATO process will look like.
Estimated Life Cycle Costs: Cost estimates should account for all costs related to the development of your initial solution, as well as the cost to operate and maintain that solution. Related costs include any impacts on other services/contracts outside your immediate contract, such as component/enterprise services, tools, pilots, etc. paid for separately by your component, OIT, or others to help meet your business need – include these under “other” costs.
These are estimated costs from a vendor response to a Request For Information.
| FY 2023 Estimated Cost | FY 2024 Estimated Cost | FY 2025 Estimated Cost | FY 2026 Estimated Cost | FY 2027 Estimated Cost | 5-Year Estimated Costs
Development | 750000 | 500000 |  |  |  | 1250000
Operations and Maintenance |  |  | 250000 | 257500 | 265225 | 772725
Other | [5 empty] | 0
TOTAL | 750000 | 500000 | 250000 | 257500 | 265225 | 2022725
What is the Cost Savings or Avoidance associated with this solution?: Provide a brief description of any potential cost savings that this solution might provide and/or cost avoidance, which describes money that you will need to spend if the solution isn't implemented. This could include old systems going away, contract hours/new FTEs not needed, or other savings, even if indirect. (2000 character limit)
This solution will reduce widget tracking time needed by about 80%. If implemented, the staff hours freed up will mean that ICPG will not need to request additional staff to implement the FORM Act in two years, translating to $684,000 in cost avoidance in that first year.
Alternative B
Alternative B: Title
Enterprise Shared Service: SHAREPOINT
Alternative B: Summary (2000 character limit)
Our project team plans to use Sharepoint's workflow process capabilities to route the widget tracking process and automate the identification and counting of the widgets. This platform already currently exists as a CMS enterprise service.
Alternative B: Acquisition Approach: Describe the approach to acquiring the products and services required to deliver the solution, including potential contract vehicles. (2000 character limit)
This solution exists in-house, with no procurement necessary.
Is your solution approved by IT Security for use at CMS (FedRAMP, FISMA approved, within the CMS cloud enclave)?:
Yes
If Above Answer is No - Is it in the process of CMS approval?: (Obtaining CMS Approval can be lengthy and solutions that do not have it or are just starting may lead to longer project timelines.)
N/A
Do you need to host your solution and where?: (Cloud - AWS, Azure, etc. or a Data Center). What, if any, type of cloud service are you planning to use for this solution (Iaas, PaaS, SaaS, etc.)?
Baltimore Data Center - Paas - SharePoint
Will your solution have a User Interface?:
Yes
Alternative B: Pros (2000 character limit)
This solution will not add any direct additional costs or infrastructure, security/privacy, and 508 compliance risks.
Alternative B: Cons (2000 character limit)
The solution does not have invoicing or visualization capabililties and one additional FTE will still need to be hired to implement the FORM Act. It is also not as customizable as the other two proposed solutions.
Estimated Life Cycle Costs: Cost estimates should account for all costs related to the development of your initial solution, as well as the cost to operate and maintain that solution. Related costs include any impacts on other services/contracts outside your immediate contract, such as component/enterprise services, tools, pilots, etc. paid for separately by your component, OIT, or others to help meet your business need – include these under “other” costs.
No direct IT costs due to utilizing enterprise service. However, starting in two years, one additional FTE will be hired to implement the FORM Act. The below is based on an average FTE cost of $171K/yr and a 3% annual increase for inflation.
| FY 2023 Estimated Cost | FY 2024 Estimated Cost | FY 2025 Estimated Cost | FY 2026 Estimated Cost | FY 2027 Estimated Cost | 5-Year Estimated Costs
Development | [5 empty] | 0
Operations and Maintenance | [5 empty] | 0
Other |  |  | 171000 | 176130 | 181413.9 | 528543.9
TOTAL | 0 | 0 | 171000 | 176130 | 181413.9 | 528543.9
What is the Cost Savings or Avoidance associated with this solution?: Provide a brief description of any potential cost savings that this solution might provide and/or cost avoidance, which describes money that you will need to spend if the solution isn't implemented. This could include old systems going away, contract hours/new FTEs not needed, or other savings, even if indirect. (2000 character limit)
This solution will reduce widget tracking time needed by about 40%. If implemented, ICPG will need to only request one additional FTE, rather than four to implement the FORM Act in two years, translating to $513,000 in cost avoidance in that first year. | [6 empty] | 1