## Slide 1
07/29/26
Segment 5 - Effective ICD-10 Implementation
<number>
Training Segment 5
Effective Implementation of ICD-10
An Informational Series on ICD-10 Planning and Assessment for State Medicaid Agencies
A Series of Topics on ICD-10 for State Medicaid Agencies:
What is ICD-10?
Regulatory Requirements
Benefits of Using ICD-10
Further Movement along the MITA Road Map - Use of Clinical Data and Interoperability
Effective Implementation of ICD-10
Potential Programmatic and Technical Problems
Impact on MITA Business Processes
Forming the Implementation Team
MMIS Funding Opportunities
Education and Training Processes
Partner and Vendor Considerations
Monitoring Progress and Post Compliance Date Actions
  ICD-10 Planning and Assessment
Notes: <number>
The move from ICD-9 to ICD-10 is a significant change for State Medicaid Agencies. It will take considerable effort for Medicaid, and every health plan and provider in the country, to successfully accomplish the transition. However, there are considerable benefits to using the new code set.
We’ve prepared a series of training sessions especially for State Medicaid agencies which provide key information about the ICD-10 code set, how to use it, how to benefit from it, and what the implementation steps are. We hope to provide the information you need to effectively implement and to benefit from this major change to the coding of health care in the United States.
There are 12 Training Segments in the entire program.
<number>

## Slide 2
07/29/26
Segment 5 - Effective ICD-10 Implementation
Show necessary steps for a Medicaid State Agency to effectively implement ICD-10
Provide guidance on who needs to be involved and when steps need to be taken
<number>
Segment 5 – Effective Implementation of ICD-10
Objectives of this Segment
Notes: <number>
This segment will provide the pathway for agencies to implement ICD-10. We will discuss specific implementation steps, who should be involved, and the timing of each step.

## Slide 3
07/29/26
Segment 5 - Effective ICD-10 Implementation
ICD-10-CM and ICD-10-PCS must be used on all transactions for services performed on and after Oct 1, 2013
Service date based, not transaction date based
Must continue to handle ICD-9 codes for services prior to Oct 1, 2013
Same implementation date for all entities
No “transition period”
<number>
Regulatory Requirements
Notes: <number>
Remember that the compliance date of Oct 1, 2013 refers to services performed on and after that date. This means that ICD-10-CM diagnosis codes, and ICD-10-PCS inpatient hospital procedure codes must be used on transactions related to services performed on and after the compliance date. Any transactions for services prior to Oct 1, 2013 will continue to use ICD-9 codes. So, you will be getting transactions with ICD-9 codes for quite a while after October 1, 2013. Note that the Oct 1, 2013 date is a single transaction date and applies to all covered entities. There is no “transition period” that allows a choice of ICD-9 or 10 codes for a transaction.
<number>

## Slide 4
07/29/26
Segment 5 - Effective ICD-10 Implementation
Developed to provide guidance to industry
Based on realistic steps and time to implement by the compliance date
Input from plans, providers, and vendors
Available at www.nchica.org
<number>
NCHICA/WEDI Timeline
Notes: <number>
WEDI and NCHICA (the North Carolina Healthcare Information and Communications Alliance, Inc.) have created a joint workgroup to develop industry timelines for the implementation of major health IT projects. The intent was to provide guidance on realistic implementation timelines, and show overlaps and resource constraints from overlapping projects. The workgroup is overseen by a steering committee consisting of plan, provider, and vendor representatives. Two major project timelines have already been completed, one from 5010 implementation and a second for ICD-10 implementation. The ICD-10 timeline was developed by groups of plans, providers, and vendors representing a broad spectrum of the industry. The timelines are developed using Microsoft Project, and are available at the NCHICA web site in both Project and PDF format. The general timelines can be used as the basis for a more detailed work plan by individual organizations.
The timelines are built to assure adequate planning, development, and testing time while meeting regulatory deadlines.
<number>

## Slide 5
07/29/26
Segment 5 - Effective ICD-10 Implementation
<number>
Overall Timeline
Notes: <number>
(Double click the timeline document and it will open.) This is the PDF version of the ICD-10 timeline. It provides dates and steps for vendors, health plans (such as Medicaid State agencies), and providers. As you can see, it provides steps and start and end dates.
<number>

## Slide 6
07/29/26
Segment 5 - Effective ICD-10 Implementation
Critical First Step is the Assessment Process
  ICD-10 is not an IT-only project
  Need to look at your business processes first
    Where are diagnosis and inpatient hospital codes currently received and used?
    How can the ICD-10 codes improve those processes?
    Where else can the codes be used to improve business processes?
  Take advantage of this time to determine what needs to be changed!
<number>
Steps for State Medicaid Agencies
Notes: <number>
We will use the health plan steps in the timeline for guidance (Steps 26-57). The first, and critical, step, is to perform a complete assessment of your business processes to determine several items. First, where are diagnosis and inpatient hospital codes currently received and used? Not only do you have to make the necessary modifications to accommodate the ICD-10 codes in systems and processes, but you now have the opportunity to determine if and how the use of ICD-10 codes can improve those processes. Secondly, look at your processes and systems to determine where the improved coding can provide improvements where codes have not yet been used. For example, there may be some claims processing edits that now can be created to better make coverage decisions using codes.
This is a critical time. It is important to take advantage of this time, before system changes are being made, to make some good decisions regarding the use of ICD-10 codes.
<number>

## Slide 7
07/29/26
Segment 5 - Effective ICD-10 Implementation
Assessment timeframe – 6 months
Involvement
  Small group of experts
  Need to be familiar with ICD-10
  Need input from all across the program
  Need access to all business areas
Should have already completed this step!
Must start ASAP, if not started already
<number>
Steps for State Medicaid Agencies
Notes: <number>
This assessment process should last around six months. A small group of experts is recommended to conduct this assessment. The experts need to be familiar with ICD-10, so make sure that you provide some training to them. The group needs to get input from all across the Medicaid program, and should have access to documentation and staff from all business areas.
According to the timeline, you should have already completed this. If not, you need to start ASAP! This is the time to make sure that your implementation process will impact all necessary areas.
<number>

## Slide 8
07/29/26
Segment 5 - Effective ICD-10 Implementation
Next Suggested Step – Business and Technical Strategy
Expected Timeframe – 1 year
Includes setting up governance structure, developing and finalizing strategies, securing budgets, and starting your implementation teams
Target completion date: July 2010
Involves entire agency – Need for trained experts
<number>
Steps for State Medicaid Agencies
Notes: <number>
The next major step in the timeline is the Business and Technical Strategy Development. Drawing on your assessment, you will determine a project governance structure (PMO, steering committees, etc.), develop the business strategy for the use of ICD-10 codes and the conversion process, then develop the technical strategy for each system that needs to be converted. This should be based on your business strategies (i.e., how ICD-10 will be used in each business process). The technical strategy will be a critical piece. A key determination that must also be made is if and how to convert history files, and how to migrate processes from the old systems to the new. The strategy step is where you determine which processes will change based on the conversion to ICD-10.
The timeline has a target completion date of July 2010. This provides enough time for the following steps of implementation, internal testing, and external partner testing.
<number>

## Slide 9
07/29/26
Segment 5 - Effective ICD-10 Implementation
Actual Implementation
Time Frame – January 2010 – Oct 1, 2013
This includes preparing requirements, system design and development, remediating provider contracts, vendor code deployment, and internal/external testing
<number>
Steps for State Medicaid Agencies
Notes: <number>
The next step in the process is the actual implementation step, which covers requirements preparation (6 months), business design and development (9 months), system design and development (18 months), and deployment and internal testing of internal systems and vendor systems (9-12 months). These time frames have been developed by large groups reaching a consensus, based on prior experience with major system changes. Timely completion of the internal deployment and testing is crucial – all partners are expected to be ready by late 2012 to do external testing.
For both the internal and external testing, end-to-end testing (from the beginning of a transaction, through processing, and to final determination) is critical. There are many moving parts to this implementation, and the only way to know if the systems are truly working correctly is to do the end-to-end testing.
We would suggest that an overall Project Management Office be created to oversee the project, as it impacts your entire program and virtually all of your systems. No one department should be tasked with this responsibility.
<number>

## Slide 10
07/29/26
Segment 5 - Effective ICD-10 Implementation
Next Steps:
End-to-end testing critical
Estimate 10 months for external partner testing
Suggest a Project Management Office (PMO) to oversee this project. It is huge.
<number>
Steps for State Medicaid Agencies
Notes: <number>
The last step in the implementation process is to test the changes made with trading partners. Because of the vast array of changes throughout the Medicaid Agency, it is critical that end-to-end testing – running processes from the beginning of a transaction throughout its lifetime to the end – be done, and that all system interfaces be tested. The national timelines also estimate that external partner testing will take 10 months, so that means all internal testing must be finished at least 10 months before Oct 1, 2013.
<number>

## Slide 11
07/29/26
Segment 5 - Effective ICD-10 Implementation
Assessment must be done first
Involves the entire agency
Is a business and a technical project
Need trained experts early on
Project management is critical
Need to “spread out” the resource and budget commitments over a long period
Internal and external testing is critical
<number>
Summary
Notes: <number>
To summarize, a thorough business and technical assessment should be done first. This will involve the entire agency – it is not just a systems change or an IT project.
Create a cadre of trained experts to do your assessments and perhaps lead strategy and project teams. This is a long-term project, and needs to be effectively managed. Try to spread out the resource and budget commitments over the long-term – don’t wait until one year before compliance to start this project.
And end-to-end external testing with partners is critical to assuring that your systems are working correctly!
<number>