## Slide 1
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Training Segment 8
Forming the Implementation Team
An Informational Series on ICD-10 Planning and Assessment for State Medicaid Agencies
A Series of Topics on ICD-10 for State Medicaid Agencies:
What is ICD-10?
Regulatory Requirements
Benefits of Using ICD-10
Further Movement along the MITA Road Map - Use of Clinical Data and Interoperability
Effective Implementation of ICD-10
Potential Programmatic and Technical Problems
Impact on MITA Business Processes
Forming the Implementation Team
MMIS Funding Opportunities
Education and Training Processes
Partner and Vendor Considerations
Monitoring Progress and Post Compliance Date Actions
  ICD-10
  Planning and
  Assessment
Notes: <number>
The move from ICD-9 to ICD-10 is a significant change for State Medicaid Agencies. It will take considerable effort for Medicaid, and every health plan and provider in the country, to successfully accomplish the transition. However, there are considerable benefits to using the new code set.
We’ve prepared a series of training sessions especially for State Medicaid agencies which provide key information about the ICD-10 code set, how to use it, how to benefit from it, and what the implementation steps are. We hope to provide the information you need to effectively implement and to benefit from this major change to the coding of health care in the United States.
There are 12 Training Segments in the entire program.
<number>

## Slide 2
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Discuss the purpose of the Implementation Team
Determine appropriate participants
Plan team schedule and responsibilities
Segment 8 – Forming the Implementation Team
Objectives of this Segment
Notes: <number>
The segment will provide specific guidance on the purpose of the ICD-10 implementation team, what type of participation is necessary for an effective team, and what specific schedule and responsibilities the team should have. We consider the formation of an ICD-10 project team necessary for a successful implementation.

## Slide 3
07/29/26
Segment 8 - Forming the Implementation Team
<number>
ICD-10 Implementation is not just an IT project
ICD-10 Implementation affects wide range of business areas:
  Benefit coverage
  Payment policies
  Provider relations
  Claims processing
  Statistical trending
  Fraud and Abuse
  Budget estimation
  Quality measurement
  Waiver programs and case management
Review of Impact Areas
Notes: <number>
We want to reiterate that this implementation project is not, and should not be thought of, as an IT project. As we have previously shown, the transition to ICD-10 affects a wide range of business areas in the Medicaid program. While the IT work is a necessary part, it should be thought of as supporting the business transition to ICD-10. The list of business areas affected is not all-inclusive, but you can see that it reaches throughout the organization. Critical business decisions on how ICD-10 will be implemented must be made in these areas as the project progresses, so that IT system changes can be made to support the business areas.
<number>

## Slide 4
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Plan the overall project
Identify areas/business units impacted
Become “ICD-10 experts” and train others
Keep management and the entire organization informed
Become advocates for benefits of ICD-10
Estimate budgets and resources needed
Manage the project and keep it on schedule
Implementation Team Functions
Notes: <number>
The implementation team will provide the overall project management in the organization throughout the implementation process. Because of the long-term nature and breadth of this project, we advocate the designation of such a team and keeping it active through the entire implementation process. This will be the focal point for implementation, and allow the day-to-day work of the organization to continue as the implementation process proceeds.
<number>

## Slide 5
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Need a mix of skills
Need individuals who understand Medicaid business processes
Need individuals who know how processes work together to accomplish tasks
Need IT systems perspective
Need people who can describe and chart processes; who understand business improvement
Need people who are willing to learn the new “language” of the ICD-10 code set
What Skills Are Needed on the Implementation Team?
Notes: <number>
A wide range of skills are needed for this team to be successful. Careful consideration must be given in selecting the right mix of team members. Individuals who have a good understanding of each of the Medicaid business processes should be included. These people should also have the ability to describe and chart these processes, and have an understanding of business process improvement. In addition, people must be included who have a good sense of how business processes interact and work together to accomplish tasks. IT professionals have to be included in this, with the understanding that they are supporting the business process changes.
These individuals must be willing to learn about this new code set and its implications.
<number>

## Slide 6
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Project planning and management skills
People ready and willing to challenge the status quo
People who can communicate the big picture of change due to ICD-10, and why changes are necessary and beneficial
An understanding of the benefits of ICD-10 and the willingness to support them
What Skills Are Needed
Notes: <number>
Individuals with strong project planning and management skills should be included as part of the team. They must be able to challenge the status quo and be willing to suggest improvements in using diagnosis and inpatient hospital procedure codes. The team should include individuals who can understand and communicate the big picture of change due to ICD-10, and why those changes are both necessary and beneficial.
It would be beneficial for the team to receive training on effective teams, and an experienced team facilitator should be part of the team to assist the team in its work.
<number>

## Slide 7
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Charter team and clearly set out responsibilities
Give team the necessary authority
Give team the necessary resources
Allow team the specific time it needs
Provide accountability to a specific executive sponsor
Let the organization know about this
Provide this as a priority project
Set the deadline and make it!
Team Processes
Notes: <number>
A clear charter with team operating rules and responsibilities will be valuable in getting the team started. There should be a high-level executive sponsor to which the team should report. The sponsor must be responsible for providing the team the necessary authority and resources to get the job done. Team members must be given the time needed to do an effective job. They need not be full-time members of the team, but they must be permitted to devote the time needed.
Also, the agency needs to inform all staff that such a team has been formed and what its responsibilities are. The project must be announced with the appropriate priority. It should be made clear to the team that there is a hard deadline to complete the project, and the team is responsible for making sure it is met.
<number>

## Slide 8
07/29/26
Segment 8 - Forming the Implementation Team
<number>
Do initial assessment and get executive level buy-in
Develop the overall project plan
Track against plan and report progress; adjust plan as necessary
Provide communication to executive levels and to the organization as a whole
Determine training schedules
Monitor vendor progress
Identify and resolve issues
Set up quality management or independent verification and validation (IV&V) process
Team Responsibilities
Notes: <number>
So, what is this team supposed to do? First, get trained on ICD-10 and do a quick organizational assessment to determine some initial parameters of cost, scope, and timing. This is necessary to provide high-level information to executives to get buy in. Then, an overall project plan should be developed, perhaps using the NCHICA/WEDI timeline as a general guide. The team then needs to work with agency staff and managers in getting each step of the process done.
The team should be held responsible for communicating the project plans and progress to the agency, and to determine both the types and schedule of ICD-10 training necessary. Vendor progress must also be monitored.
It is critical for the team to continue to monitor progress, identify issues (resource constraints, conflicts with other priorities, unexpected changes in budgets or other circumstances), and resolve them. One critical task may be to set up some sort of internal product and system quality management , or an outside independent verification and validation (IV&V) process to provide assurance that work products will perform as desired.
<number>

## Slide 9
07/29/26
Segment 8 - Forming the Implementation Team
<number>
A dedicated implementation team is critical to this project
The team needs a wide variety of skills
A well-documented set of roles and responsibilities is necessary for a successful team
The team should be charged with assuring the compliance date it met
Summary
Notes: <number>
We strongly recommend a dedicated ICD-10 implementation team be formed to begin the assessment process, determine training needs, monitor agency and vendor progress, and assure the project is moving along on time and is producing quality products. This team needs a wide variety of skills to do an effective job. Make sure the team has the tools, the responsibility, and the authority to get the job done.
<number>